## Sheet1
Date | Work Type | Task | Context | Issues Faced | Status
2025-12-07 | Remote | Make initial research about TIPs | Questions asked for this initial search: 1) Definition of TIPs 2) Common feature list that is included in all TIPs 3) Unique feature list for TIPs 4) Business model 5) Famous TIPs |  | Pending: The final result can be found in a folder called Core Research
13/7/2025 | Remote | Make a more strutured study plan for the project. | Steps to do so: 1) Ask more questions 2) Look at the previous files and integrate them into the final research before deleting them |  | DONE: Integrated the useful parts of the previous research into the current Final Research and deleted the unneeded work
13/7/2025 | Remote | Based on your final research, define what each member will do and their responsibilities |  |  | DONE: The final result can be found in a folder called Research For Team Leading
13/7/2025 | Remote | Answer the upcoming question: Threat Intelligence Platform (TIP), Network Scanner / NDR, SIEM what else????? |  |  | DONE: The final result can be found in a folder called Extra Research
14/7/2025 | Remote | LLMs research