## Sheet1
Date | Work Type | Task | Context | Issues Faced | Status
2025-12-07 | Remote | Make initial research about TIPs | Questions asked for this initial search: 1) Definition of TIPs 2) Common feature list that is included in all TIPs 3) Unique feature list for TIPs 4) Business model 5) Famous TIPs |  | Pending: The final result can be found in a folder called Core Research
13/7/2025 | Remote | Make a more strutured study plan for the project. | Steps to do so: 1) Ask more questions 2) Look at the previous files and integrate them into the final research before deleting them |  | DONE: Integrated the useful parts of the previous research into the current Final Research and deleted the unneeded work
13/7/2025 | Remote | Based on your final research, define what each member will do and their responsibilities |  |  | DONE: The final result can be found in a folder called Research For Team Leading
13/7/2025 | Remote | Answer the upcoming question: Threat Intelligence Platform (TIP), Network Scanner / NDR, SIEM what else????? |  |  | DONE: The final result can be found in a folder called Extra Research
14/7/2025 | Remote | LLMs datasets research |  |  | DONE: The final result is stored at Data Engineering Research/ LLM Dataset 1 and 2 and final
14/7/2025 | Remote | Phishing datasets research |  |  | DONE: The final result is stored at Data Engineering Research/ Domain Monitoring phising analysis Idea and Datasets
15/8/2025 | Remote | Try to implement a data pipeline to extract the CVEs and try to update the updated CVEs from the old DB using cumulative table design |  |  | FAILED: My humble knowledge about the security data failed me, and the api usage isnt clear for me as reddit's api. This task needs to be planned for and divided into sub tasks.
15/8/2025 | Remote | Make a Data Dictionary for each resource that you gonna include in your NLP Dataset